## NoteGen Architecture Status
Operative-Note Generation - Status vs. Planned Architecture
Updated 2026-09-29. Maps actual progress against the 6-layer architecture in neurosurgery_notegen_architecture.md, grounded in real notebook runs (smoketest_orena_procedure, benchmark_endofm_pitvis, notegen_colab_demo), not the original design intent alone. Status colors: green = built and validated, amber = partially built, red = built but producing poor/concerning results, grey = not built.
Architecture Layer | Status | What's Actually Built | Evidence (Notebook / Run) | Gap / Next Step
Layer 1 - Input | Built & validated | Raw video obtained for Stage-1 scope (pituitary/eTSA endoscopic): PitVis-2023 (25 videos + step/instrument CSV labels) on Drive. Separately, 5 orena-procedure (HeiCo) videos downloaded for an unrelated frame-track smoke test on the same Endo-FM backbone. | smoketest_orena_procedure_with_output.ipynb (5 videos found, all extracted); benchmark_endofm_pitvis.ipynb Section 2 (25 videos discovered, common_ids matched to annotations) | None for Stage 1. Stage 2 (open cranial/microscope) has no video source at all yet.
Layer 2 - Adapted Perception Backbone | Partially built | Endo-FM ViT-B/16 TimeSformer carried forward AS-IS (checkpoint loads, all keys match). The 'adaptation' step the architecture doc calls for - DAPT -> TAPT -> PEFT on neurosurgery video - has NOT been done; this is still the stock general-endoscopy pretrained backbone. No camera/modality adapter exists. | smoketest_orena_procedure: 'Loaded Endo-FM weights: <All keys matched successfully>', real 8-frame clips -> (15,768) features; smoketest_pitvis (earlier): (40,768) on real PitVis frames | Continued self-supervised pretraining (DAPT) on unlabeled PitVis/neurosurgery video is designed but not implemented anywhere in this project.
Layer 3 - Structured Perception (Phase/Step) | Not built | No trained phase/step-recognition head. The notegen demo uses PitVis's OWN ground-truth step labels directly (facts_from_labels()) as a stand-in. For unlabeled video, facts_from_perception()'s phase windowing is a fixed-time-window placeholder, not real phase segmentation. | notegen/facts.py; video_01 taxonomy load: '15 steps, 21 instruments, 78 phase(s)' (all from PitVis's own CSV, not predicted) | Train a real step-recognition head per the architecture doc (target: step-recognition F1 >= 0.80, matching Das et al.) before trusting output on any video without hand labels.
Layer 3 - Structured Perception (Segmentation / Detector-Tracker) | Partially built | CountGD (open-vocab detector) + SAM 2.1 (masklet tracker) infrastructure exists and is reused from the unrelated ORena FOCUS frame-track counting work (code/INTEGRATION.md), not re-vendored. Not validated specifically for the notegen use case - the demo run used PitVis's ground-truth instrument labels instead of live detection. | counting/countgd_detector.py, counting/sam2_tracker.py (from 2026-09-01_frame-countgd-sam2-qwen3.5-9b) | Run facts_from_perception() (the actual CountGD+SAM2 path) end-to-end on a video with NO labels and compare its detected instrument set against PitVis ground truth, to know how much it can be trusted.
Layer 4 - Language Generation (drafting) | Built, poor results | Qwen/Qwen3.5-9B + A_s189 LoRA adapter used as a cold-start checkpoint. A_s189 was trained for a DIFFERENT task (ORena FOCUS counting/VQA, frame track) - NOT note generation. Real run: mean note_format=0.80 (inflated by one all-placeholder completion scored 1.00), mean note_grounding=0.10. Confirmed specific failure: model output instruments 'Specimen bag'/'external drain' - not real PitVis instruments, but literal class names from A_s189's original counting task - cross-task vocabulary leakage, not random noise. | notegen_colab_demo_with_output.ipynb Sections 3-4 (5-phase run on PitVis video_01) | This project's own GRPO run (train_grpo.effective.sh) has not happened yet - no training dataset built. Until it does, treat this checkpoint as a plumbing test, not a working note generator.
Layer 5 - Grounding/verification module | Partially built | Implemented as a GRPO REWARD signal (note_grounding ORM: set-F1 of claimed vs. ground-truth instruments/steps), not yet as an inference-time gate. It correctly caught the cross-task vocabulary leakage above when run standalone as a scorer - i.e. the mechanism works as a detector - but a bad note is not currently blocked from reaching output. | code/rlvr/notegen_plugin.py (NoteGroundingORM), scored the real run's completions | Wire this as an actual pre-output filter/gate, not only a training-time reward, if this is ever used beyond a research demo.
Layer 6 - Note Assembly | Partially built | RCS 'Good Surgical Practice' 6-field template implemented and used in prompts (template.py). Clip-level -> phase-level generation implemented (one generation per phase). Phase-level -> full-procedure is a plain concatenation (_assemble()), NOT a second summarizing pass. Found gap: the format reward (note_format ORM) does not yet penalize an all-placeholder '...' completion - it scored one such case a perfect 1.00 in the real run. | code/models/qwen3vl_finetune/src/notegen/template.py, service.py's _assemble(); notegen_colab_demo_with_output.ipynb phase 0 (0s-2s) - unfilled template scored note_format=1.00 | Add a real summarizing merge pass (per architecture doc); fix note_format to check for actual content, not just tag presence/order.
Layer 7 - GRPO reward | Two terms: note_format (tag presence/order) + note_grounding (instrument/step set-F1 -- found to structurally collapse to recall-only, not real F1, since it can only match gold-vocabulary terms). | §5.5: seven terms -- R_format (gate) + R_ground (ID grounding) + P (precision) + Rec (coverage, weighted by clinical importance) + R_cal (Brier calibration) + R_corrupt (confidence must drop when evidence is corrupted) + R_unk (reward honest "unidentified" labeling) -- combined as R_format · [weighted sum − length penalty]. | The old reward can't teach the model to KNOW when it's unsure, can't verify precision separately from recall, and has no mechanism against confident hallucination on corrupted/out-of-distribution frames -- exactly the vocabulary-leakage failure already found in this project's own test run.
Output - Human-in-the-Loop | Partially built | Draft-only framing is maintained as project POLICY (COMPLIANCE.md: no autonomous publishing, human sign-off required) - this is a documentation/discipline commitment, not a technical gate in the code itself. | COMPLIANCE.md clinical-safety checklist | No confidence/uncertainty flagging per section exists yet, as the architecture doc calls for.
Overall verdict | Infrastructure-stage, not generation-quality-stage. Layers 1-2 (input, frozen backbone) are solid. Layers 3-6 mostly have SOMETHING built (reusing the unrelated frame-track CountGD/SAM2/reward infrastructure), but the one component that actually generates note text (Layer 5) is currently a wrong-task LoRA adapter with no note-generation training of its own, and produces low-grounding output as a direct, expected consequence - not a surprise, and not yet evidence against the architecture. The real value of this round of testing was diagnostic: a specific, reproducible failure mode (cross-task vocabulary leakage) and a reward-design gap (format reward not content-aware), both fixable before the next step, which is building the GRPO training dataset this project still doesn't have.